## Status
Task | Owner | Status | Last Update
Interaction design prototype | George | Completed | Completed full taxonomy
Templates library creation | Lisa | In progress | Setting up templates, 50% completed
Graphics design | John | In progress | Designed graphics, 20% completed
Partner interviews | Alexandra | Not Started | Waiting for authorization to start partner interviews
UI flow design | Lisa | Not Started | Waiting for templates completions
User Flow review | George | Not Started | Waiting for first UI draft completion
Investors presentation | George | Completed | Meeting completed

## Stakeholders
Stakeholder | Role | Email address | Interest | Influence | Communication rule | Notes | Email Subject | Message Header | Message Footer | Response
Brandon | Team member | daskalosmathitis@gmail.com | Core team | Core team | Core team | Email any update | Recent update | Hi Brandon, somebody has put an update, please have a look. | Thank you for your amazing impact to this project | Email Sent
Lisa | Team member | d.askalosmathitis@gmail.com | High | High | Manage closely | Daily email including update notes | Your daily update | Hi Lisa, somebody has put an update, please have a look. | Thank you for your amazing inputs to this project | Email Sent
John | Team member | da.skalosmathitis@gmail.com | High | High | Manage closely | Daily email including update notes | Your daily update | Hi John, somebody has put an update, please have a look. | Thank you for your amazing inputs to this project | Email Sent
Alexandra | Team member | das.kalosmathitis@gmail.com | Core team | Core team | Core team | Email any update | Recent update | Hi Alexandra, somebody has put an update, please have a look. | Thank you for your amazing impact to this project | Email Sent
James | Director | dask.alosmathitis@gmail.com | Core team | Core team | Core team | Email any update | Recent update | Hi James, somebody has put an update, please have a look. | Thank you for your amazing impact to this project | Email Sent
Rita | Program Manager | daska.losmathitis@gmail.com | High | High | Manage closely | Daily email including update notes | Your daily update | Hi Rita, somebody has put an update, please have a look. | Thank you for your amazing inputs to this project | Email Sent
Martha | Project Manager | daskal.osmathitis@gmail.com | Low | Low | Monitor | Monthly email without including update notes | Your Monthly update | Hi Martha, somebody has put an update, please have a look. | Thank you for being part of this project | Email Sent
Jacob | Partner Manager | daskalo.smathitis@gmail.com | High | Low | Keep informed | Weekly email including update notes | Your weekly update | Hi Jacob, somebody has put an update, please have a look. | Thank you for your amazing support to this project | Email Sent
Max | Team Leader | max.lead@gmail.com | Low | High | Keep satisfied | Monthly email including update notes | Your monthly update | Hi Max, somebody has put an update, please have a look. | Thank you for your support to this project | Email Sent
Sai | Team member | saikrishna.t4166@gmail.com | High | Low | Keep informed | Weekly email including update notes | Your weekly update | Hi Sai, somebody has put an update, please have a look. | Thank you for your amazing support to this project | Email Sent
Vivek | Director | vivekmuniswamy.a@gmail.com | Low | High | Keep satisfied | Monthly email including update notes | Your monthly update | Hi Vivek, somebody has put an update, please have a look. | Thank you for your support to this project | Email Sent

## Communication Log
05-26-2020 ¦ 11:24:37 | daskalosmathitis@gmail.com | Update on our team project
05-26-2020 ¦ 11:24:39 | da.skalosmathitis@gmail.com | Update on our team project
05-26-2020 ¦ 11:24:42 | das.kalosmathitis@gmail.com | Update on our team project
2021-04-29T19:21:18Z | saikrishna.t4166@gmail.com | Your weekly update
29-04-2021¦19:23:06 | saikrishna.t4166@gmail.com | Your weekly update
29-04-2021 ¦ 19:32:32 | saikrishna.t4166@gmail.com | Your monthly update
29-04-2021 ¦ 19:40:57 | saikrishna.t4166@gmail.com | Your monthly update
29-04-2021 ¦ 21:38:52 | saikrishna.t4166@gmail.com | Your weekly update
29-04-2021 ¦ 21:39:37 | saikrishna.t4166@gmail.com | Your weekly update
29-04-2021 ¦ 21:45:57 | vivekmuniswamy.a@gmail.com | Your monthly update
29-04-2021 ¦ 23:17:09 | saikrishna.t4166@gmail.com | Your weekly update
30-04-2021 ¦ 07:04:00 | saikrishna.t4166@gmail.com | Your weekly update